## Executive Summary
Nexus HRMS — SRS Addendum Compliance Audit
Audit scope: Recruitment, Onboarding, Project Mgmt, Performance, Exit, Admin Integration, Security
Compliance KPIs
Total Requirements | 44
Fully Implemented | 1
Partially Implemented | 14
Placeholder Only | 3
Missing | 26
Compliance Rate | 2.3%
At-Risk Rate (Missing + Placeholder) | 65.9%
Status Breakdown by SRS Section
Section | Full | Partial | Placeholder | Missing | Total | Compliance %
Recruitment | 1 | 3 | 2 | 2 | 8 | 12%
Onboarding | 0 | 4 | 0 | 0 | 4 | 0%
Project Mgmt | 0 | 4 | 0 | 5 | 9 | 0%
Performance | 0 | 0 | 0 | 3 | 3 | 0%
Exit | 0 | 2 | 1 | 5 | 8 | 0%
Super Admin | 0 | 1 | 0 | 3 | 4 | 0%
Tenant Admin | 0 | 0 | 0 | 5 | 5 | 0%
Security | 0 | 0 | 0 | 3 | 3 | 0%
TOTAL | 1 | 14 | 3 | 26 | 44 | 2.3%
🚨 Critical Issues (P0 — Runtime Crashes)
• 6 API surfaces call Prisma models that don't exist in schema.prisma — every request crashes or returns mock data
• Affected: Preboarding, Exit Workflow, OKR API, Exit Interview, Engagement Surveys, AI Admin Console
• Timesheet schema is broken (project/task are Strings not FKs; @@unique blocks multi-project/day logging)
• Project Confidentiality fails open — any auth user can read any project's financials (REQ-SEC-11)
• Timesheet Immutability fails open — approved+invoiced timesheets can be edited/deleted by anyone (REQ-SEC-12)

## Compliance Matrix
SRS Addendum Compliance Matrix — All Requirements
Filter the table below by Section, Status, or Priority. Use Excel's filter dropdowns on row 4.
Section | Req ID | Status | Requirement | Priority | Evidence (file paths / API routes) | Gap (what's missing)
Recruitment | REQ-REC-01 | Full | Manpower Requisitions (Requests to Hire) | P3 | Requisition model + /api/requisitions/** + UI form (Manpower Requisitions page) | Minor UX: dept/designation are free-text inputs instead of dropdowns
Recruitment | REQ-REC-02 | Partial | Tenant Admin Approval (budget/headcount thresholds) | P2 | 3-stage approval workflow (pending → manager_approved → hr_approved → budget_approved ¦ rejected); Company.maxEmployees & CompanyGroup.maxEmployees exist as caps | No automatic trigger based on budget/headcount thresholds; no role guard on PATCH endpoint; salaryBudget is free-text String (no numeric comparison)
Recruitment | REQ-REC-03 | Missing | Multi-Currency Budgeting (CTC local + Group base display) | P1 | Requisition.salaryBudget is free-text String; Offer.offeredCurrency/offeredCTC exist; CurrencyConfig + ExchangeRate models exist but unused in recruitment | No numeric CTC capture, no FX conversion to group base currency, no UI display of converted amounts
Recruitment | REQ-REC-04 | Placeholder | AI Resume Parsing (multi-lingual) | P2 | /api/recruitment-ai action=parse_resume exists but returns hardcoded 'John Smith' object | No file upload, no ZAI call, no language detection, no PDF/DOCX parsing
Recruitment | REQ-REC-05 | Placeholder | AI Matching (skills, experience, semantic) | P2 | /api/recruitment-ai action=score_candidates returns 4 hardcoded entries; ignores jobPostingId parameter | No real AI matching engine; no semantic analysis; no skill vector comparison
Recruitment | REQ-REC-06 | Missing | Multi-Lingual Job Posting + AI auto-translate | P2 | JobPosting model has only title/description/requirements — no language field | No translation pipeline; no i18n library installed in project
Recruitment | REQ-REC-07 | Partial | Interview Scheduler (calendar + multi-timezone) | P3 | Interview model with date/time/duration/meetingUrl; scheduler dialog in AI Interview page | No Google/Outlook/iCal integration; time stored as raw String with no timezone metadata; Company.timezone never consulted
Recruitment | REQ-REC-08 | Partial | AI Interview Insights (Fit Score + red-flag risks) | P3 | Real ZAI evaluation in /api/ai-interview/evaluate returns overall/communication/grammar/skill scores; ProctoringLog tracks red-flags (tab_switch, face_not_detected, audio_anomaly, etc.) | No 'Fit Score' label; analyzes text transcripts only, not audio/video recordings
Onboarding | REQ-ONB-01 | Partial | Dynamic Offer Letters (GDPR/APAC compliant clauses) | P2 | Offer model + CRUD + status workflow (draft → pending_approval → approved → sent → accepted/rejected) | No PDF generation; no country detection; no GDPR/APAC legal clause injection; no template model; no e-signature
Onboarding | REQ-ONB-02 | Partial | Onboarding Task Checklist (IT/HR/Admin) | P2 | OnboardingTask model with category field (general, it_setup, hr_docs, training); CRUD endpoints | No admin_desk category; not wired to AssetAssignment for laptop/access provisioning; categories are free-text not enum
Onboarding | REQ-ONB-03 | Partial | AI Onboarding Buddy (24/7 native-language) | P3 | Generic HR chatbot via ZAI exists at /api/ai-chat; AIChatLog persists sessions | No buddy persona; no onboarding-specific KB; no native-language selector; same chatbot as general HR queries
Onboarding | REQ-ONB-04 | Partial | Cross-Group Project Assignment | P2 | ProjectAllocation schema permits cross-company assignment (no constraint); Employee.companyId + Project.companyId exist | No UI surface (Team tab is read-only); no audit; home sub-company not visible in allocation UI
Project Mgmt | REQ-PM-01 | Partial | Projects linked to Clients or Internal Initiatives | P2 | Project model has clientId FK + projectType enum (internal, client, r_and_d, support); POST accepts both fields | Client dropdown NOT rendered in Create/Edit form — field silently sent as empty
Project Mgmt | REQ-PM-02 | Partial | Budget & Multi-Currency per Project | P2 | Project.currency/budgetAmount/billingRate/costRate; Client.billingCurrency; ExchangeRate model exists | Currency list hardcoded to 4 values (USD/EUR/INR/GBP); billingRate/costRate NOT exposed in UI; no FX in PM context
Project Mgmt | REQ-PM-03 | Missing | Cross-Company Allocation (Tenant Admin) | P2 | ProjectAllocation schema allows it (no company-scoping constraint); POST endpoint accepts any employeeId | Allocation POST never called from UI; no Tenant Admin cross-company workflow; no validation; no audit
Project Mgmt | REQ-PM-04 | Missing | Visual Gantt Charts (group resource availability) | P3 | No Gantt library in package.json (only recharts); no /dashboard/gantt page; no /api/gantt endpoint | Entire feature missing — no timeline visualization, no group resource view, no DnD scheduling
Project Mgmt | REQ-PM-05 | Missing | AI Capacity Planning (burnout/under-allocation) | P3 | No Capacity/Workload/Burnout model; no /api/capacity route; ZAI not used in PM context | Entire feature missing — no workload aggregation, no AI analysis, no risk suggestions
Project Mgmt | REQ-PM-06 | Missing | Utilization Rates (billable vs non-billable) | P2 | ProjectTask.isBillable + ProjectAllocation.billingStatus exist; no aggregation; Timesheet has no billable flag | Entire feature missing — no per-employee or per-sub-company utilization tracking; no /api/utilization endpoint
Project Mgmt | REQ-PM-07 | Partial | Timesheets (log hours against projects/tasks) | P1 | Timesheet model + UI + POST/PATCH endpoints; weekly summary on dashboard | project/task are plain String? (NOT FKs to Project/ProjectTask); @@unique([employeeId, date]) blocks multi-project/day entries
Project Mgmt | REQ-PM-08 | Partial | Timesheet Approval Workflow (PM + Tenant Admin) | P2 | Timesheet.status (draft/submitted/approved/rejected) + approvedBy/approvedAt; PATCH endpoint stamps approver | No PM-specific role distinction (any manager can approve); no Tenant Admin group-wide pending view; no rejection reason
Project Mgmt | REQ-PM-09 | Missing | Multi-Currency Invoicing from timesheets | P2 | No Invoice or InvoiceLineItem model; no /api/invoices route; no /dashboard/invoices page | Entire feature missing — no invoice generation, no FX-to-client-currency conversion, no draft persistence
Performance | REQ-PER-01 | Missing | OKR Cascade (Company → SubCo → Project → Individual) | P2 | Goal model is employee-only flat (no companyId, projectId, or parent-child); OKR API exists but calls prisma.oKR (BROKEN — model not in schema) | OKR model + cascade hierarchy entirely missing; existing OKR API is non-functional placeholder
Performance | REQ-PER-02 | Missing | AI Performance Nudges (30-day feedback) | P3 | No nudge/remindManager/feedbackReminder logic anywhere; no scheduler/cron jobs; performance-ai route only does insights/predictions | No feedback-gap detection; no scheduled reminder job; no AI nudge generator
Performance | REQ-PER-03 | Missing | Project-Based Feedback (clients, multi-lingual) | P3 | Feedback model only handles employee-to-employee (fromId/toId/type); no clientId/projectId; no ProjectFeedback model | No client/project feedback model; no submission endpoint; no multi-lingual UI; no auto-translation
Exit | REQ-EXIT-01 | Missing | Employee Self-Service Resignation | P2 | Admin-only /separation page; self-service.tsx has no resignation tab; /api/exit-workflow references db.exitRequest (BROKEN — model missing) | No employee-facing resignation initiation; admin-only separation page exists instead
Exit | REQ-EXIT-02 | Placeholder | Automated Clearance Workflow (IT/Finance/PM triggers) | P2 | Seeded 'Offboarding Workflow' WorkflowDefinition template with 4 steps (Manager/IT/Finance/HR clearance) | Template only — no code instantiates WorkflowInstance on Separation creation; no automated triggers
Exit | REQ-EXIT-03 | Missing | Identify Active Projects on Resignation | P2 | ProjectAllocation model exists but no logic in /api/separation queries it on Separation creation | No code path enumerates exiting employee's active project allocations
Exit | REQ-EXIT-04 | Missing | PM Must Reassign Tasks Before Exit Completes | P2 | ProjectTask.assignedToId exists; /api/separation/[id] allows status=completed with no validation | No guard, validation, or UI requiring task reassignment prior to exit completion
Exit | REQ-EXIT-05 | Partial | Digital Exit Interview Forms (multi-lingual) | P2 | API exists at /api/exit-interview with full CRUD shape — but calls prisma.exitInterview (BROKEN); Separation.exitInterview is free-text String | ExitInterview model missing (API crashes); no multi-lingual form framework; no structured questions
Exit | REQ-EXIT-06 | Missing | AI Sentiment Analysis on Exit Interviews | P3 | No ZAI call processes exit interview text; only hardcoded sentiment strings in engagement module | No AI sentiment analysis on exit interviews; no trend aggregation
Exit | REQ-EXIT-07 | Partial | Final Settlement (leave, bonus, severance) | P2 | FNFCalculation model + /api/fnf + /api/payroll/fnf; manual form with pendingSalary, leaveEncashment, bonus, noticeRecovery, etc. | No auto-calc from LeaveBalance; no severance field; no pro-rated bonus engine; separationId optional (not enforced)
Exit | REQ-EXIT-08 | Missing | Service/Relieving Letters (labor-law compliant) | P3 | Only hardcoded relievingLetterIssued boolean checkbox in dead code; no PDF generation; no template model | No letter generation whatsoever; no compliance rules engine
Super Admin | SA-1 | Missing | Global Talent Pool (cross-region candidate suggestions) | P2 | No Candidate model — denormalized across JobApplication/Offer/InterviewSession; /api/candidates returns demo data on every call | No first-class Candidate entity; no cross-tenant search UI; no API to surface candidates globally
Super Admin | SA-2 | Missing | Project Profitability Dashboard (currency normalized) | P2 | Project has currency/budgetAmount/billingRate/costRate but NO billingCurrency field; PLATFORM_BASE_CURRENCY='USD' hardcoded; src/lib/currency.ts has formatCurrency but NO convertCurrency() | No Most-vs-Least-Profitable aggregation; no FX normalization layer; no /api/super-admin/profitability endpoint
Super Admin | SA-3 | Partial | Audit Trails + Context Swapping (impersonation) | P2 | /api/audit/context-swap writes AuditLog row with action=CONTEXT_SWAP; /api/super-admin/audit-logs paginates + filters | Only logs the swap event — no impersonation UI; no drill-down for 'why was this candidate rejected' or 'why was budget overridden'
Super Admin | SA-4 | Missing | System Config (cost-per-hire, utilization thresholds) | P3 | No SystemConfig model; PLATFORM_BASE_CURRENCY hardcoded with comment 'could be moved to a SystemConfig table later' | No configurable platform metrics; FeatureFlag.config is freeform JSON unused by cost-per-hire logic
Tenant Admin | TA-1 | Missing | Group Resource View + Drag-and-Drop from Bench | P3 | No 'bench' / 'unallocated' flag on Employee; no centralized group-employee page; no DnD library (react-dnd, @dnd-kit) | No bench concept; no cross-company allocation UI; no DnD from bench → project
Tenant Admin | TA-2 | Missing | Recruitment Budgeting + Freeze Hiring | P2 | No recruitmentBudget/hiringFrozen/hiringLimit fields on Company or CompanyGroup; only Tenant.status='suspended' exists | No recruitment-cost aggregation; no per-sub-company hiring-freeze toggle
Tenant Admin | TA-3 | Missing | Cross-Billing Visibility (internal resource sharing) | P3 | Zero matches for cross-billing/internal-billing anywhere; no InterCompanyTransfer/InternalBilling model | No inter-company billing model; no report; no UI
Tenant Admin | TA-4 | Missing | Exit Oversight (senior management resignations) | P2 | Separation model has no isCritical/isSeniorManagement/designationLevel flag; zero matches for critical exit | No seniority classification on Separation; no instant-oversight view
Tenant Admin | TA-5 | Missing | AI Group Insights (deadline-miss predictions) | P3 | /api/reports/ai returns flightRisk/attrition (heuristic, not real AI); no 'Project X likely to miss deadline' prediction | No project-deadline AI; no transfer-recommendation AI
Security | REQ-SEC-10 | Missing | Candidate Data Privacy (GDPR/CCPA, 2-yr purge) | P2 | No retentionUntil/anonymizedAt fields on JobApplication/Offer/InterviewSession; no retention job/scheduler; no DSAR endpoint | No automated 2-year purge/anonymization; no consent management; no right-to-be-forgotten endpoint
Security | REQ-SEC-11 | Missing | Project Confidentiality (no cross-project financials) | P1 | /api/projects/[id] returns full financials to ANY authenticated user; only check is verifyToken; no ProjectMember model | No project-level RBAC; any auth user can read any project's financials
Security | REQ-SEC-12 | Missing | Timesheet Immutability (lock when approved+invoiced) | P1 | Timesheet has only status/approvedBy/approvedAt — no invoiced/locked/version fields; PUT/PATCH/DELETE open to all; no TimesheetHistory model | Approved/invoiced timesheets can be edited or deleted freely by any auth user; no Super-Admin override path

## P0 Broken Models
P0 — Broken Prisma Models (Runtime Crashes)
These API surfaces reference Prisma models that do NOT exist in prisma/schema.prisma. Every request either throws TypeError or silently falls back to mock data. Fix first.
Surface | Missing Model(s) | Affected Route(s) | Symptom | Fix Approach
Preboarding pipeline | PreboardingCandidate | /api/preboarding/** + /dashboard/preboarding | UI silently shows demo data — API call falls into catch block | Add PreboardingCandidate model to prisma/schema.prisma + migration
Exit Workflow | ExitRequest | /api/exit-workflow/** + exit-workflow.tsx | Every call throws TypeError (db.exitRequest is undefined) | Add ExitRequest model OR remove dead routes and use Separation model
OKR API | OKR, KeyResult | /api/okrs/** + /okr (no page exists) | Runtime error — prisma.oKR is not a function | Add OKR + KeyResult models with cascade fields (companyId, projectId, parentOkrId)
Exit Interview | ExitInterview | /api/exit-interview/** | Runtime error — prisma.exitInterview is not a function | Add ExitInterview model linked to Separation
Engagement Surveys | Survey, SurveyResponse, Recognition | /api/engagement/** + /dashboard/engagement | Runtime error — all engagement endpoints crash | Add Survey, SurveyResponse, Recognition models
AI Admin Console | AIConfig, AIPromptLog | /api/ai-admin/** + /dashboard/ai-admin | Entire AI Admin Console crashes — prisma.aIConfig is not a function | Add AIConfig + AIPromptLog models (only AIChatLog currently exists)

## Cross-Cutting Gaps
Cross-Cutting Gaps (block multiple requirements)
Foundational gaps that, when fixed, unblock multiple SRS requirements simultaneously. Highest leverage.
Gap | Affects (Req IDs) | Current State | Fix Approach | Priority
No i18n library installed (no next-intl / react-intl / i18next) | REQ-REC-06, REQ-ONB-03, REQ-PER-03, REQ-EXIT-05 | All UI strings are hardcoded English; Tenant.language and Company.language fields are essentially inert | Install next-intl + add src/locales/{en,es,fr,de,pt-BR,hi,zh,ja}/common.json + wire NextIntlClientProvider in app/layout.tsx | P1
No convertCurrency() utility — ExchangeRate table exists but is never consumed | REQ-REC-03, REQ-PM-09, SA-2, TA-3 | src/lib/currency.ts only has formatCurrency (locale display); PLATFORM_BASE_CURRENCY hardcoded to 'USD' | Add convertCurrency(amount, from, to, date?) to src/lib/currency.ts that reads latest ExchangeRate row | P1
No Candidate first-class model | SA-1, REQ-SEC-10 | Candidate info denormalized into JobApplication.candidateName/Email/Phone + Offer.candidateId/Name/Email | Promote to a first-class Candidate model with tenantId, retentionUntil, anonymizedAt fields | P2
No project-level RBAC (ProjectMember / ProjectPermission models) | REQ-SEC-11 | src/lib/roleAccess.ts is module-level only; /api/projects/[id] returns financials to any auth user | Add ProjectMember + ProjectPermission models; gate financial fields in /api/projects/[id] GET | P1
No Invoice model | REQ-PM-09, SA-2 | ProjectMilestone.invoiceStatus is a string status only — no invoice record is ever created | Add Invoice + InvoiceLineItem models; build generation pipeline from approved Timesheets + ProjectAllocation.billingRate | P2
No Utilization model or /api/utilization endpoint | REQ-PM-06 | ProjectTask.isBillable + ProjectAllocation.billingStatus exist but are never aggregated | Add Utilization model + aggregation endpoint computing billable vs non-billable hours per employee/sub-company | P2
No Gantt library in package.json | REQ-PM-04 | Only recharts ^3.8.1 installed; no frappe-gantt, @bryntum/gantt, dhtmlx-gantt | Install frappe-gantt or @bryntum/gantt; build /dashboard/gantt page + /api/gantt endpoint | P3
No scheduler/cron for nudges, retention purge, auto-task triggers | REQ-PER-02, REQ-SEC-10, REQ-EXIT-02 | Only Next.js route handlers exist; no Vercel Cron configuration | Use Vercel Cron + /api/cron/* routes for: 30-day feedback nudges, 2-year candidate purge, separation clearance triggers | P2
Timesheet schema broken — project/task are Strings (not FKs); @@unique blocks multi-project/day | REQ-PM-07, REQ-PM-08, REQ-PM-09, REQ-SEC-12 | Timesheet.project and Timesheet.task are String? not FK; @@unique([employeeId, date]) allows only 1 entry/day | Migrate Timesheet.project → projectId FK; Timesheet.task → taskId FK; drop per-day unique constraint | P1
AI routes use mock data instead of real ZAI calls | REQ-REC-04, REQ-REC-05, REQ-PER-02, TA-5 | parse_resume returns hardcoded 'John Smith'; score_candidates returns 4 hardcoded entries; reports/ai is heuristic+random | Replace mocks with real z-ai-web-dev-sdk calls; add capacity-ai and sentiment-ai routes | P2
Multi-tenant row scoping inconsistent across APIs | Multi-Tenancy (cross-cutting) | Most APIs verify JWT but don't re-scope DB queries by decoded.tenantId (e.g., /api/timesheets has no tenant filter; /api/projects/[id] has no tenant check) | Add tenant scoping middleware/helper that re-scopes every DB query by decoded.tenantId | P2

## Remediation Roadmap
Remediation Roadmap — Phased Delivery Plan
Sequenced phases — each phase's tasks unlock later phases. P0 (stabilize) → P1 (foundations) → P2 (AI) → P3 (UX).
Phase | Task | Unlocks / Delivers | Effort | Dependencies
Phase 1 — Stabilize | Fix 6 broken Prisma models (add to schema.prisma + migrate) | Unblocks: REQ-PER-01, REQ-EXIT-05, REQ-EXIT-01, Engagement, AI Admin | 2-3 days | None
| Fix Timesheet schema (project/task → FK, drop @@unique) | Unblocks: REQ-PM-07, REQ-PM-08, REQ-PM-09, REQ-SEC-12 | 1 day | None
| Add ProjectMember model + project-level RBAC on /api/projects/[id] | Delivers: REQ-SEC-11 | 2 days | None
| Add Timesheet lock fields (locked, invoicedStatus) + Super Admin override | Delivers: REQ-SEC-12 | 1 day | Timesheet schema fix
| Add convertCurrency() utility + wire ExchangeRate table | Unblocks: REQ-REC-03, REQ-PM-09, SA-2, TA-3 | 1 day | None
| Install next-intl + create locale skeleton | Unblocks: REQ-REC-06, REQ-ONB-03, REQ-PER-03, REQ-EXIT-05 | 2 days | None
Phase 2 — Foundations | Add Invoice + InvoiceLineItem models + /api/invoices | Delivers: REQ-PM-09 | 3-4 days | convertCurrency + Timesheet schema fix
| Add Candidate first-class model + /api/candidates refactor | Delivers: SA-1, REQ-SEC-10 (partial) | 2-3 days | None
| Add Utilization model + /api/utilization aggregation endpoint | Delivers: REQ-PM-06 | 2-3 days | Timesheet schema fix
| Add OKR + KeyResult models with cascade fields | Delivers: REQ-PER-01 | 2-3 days | Phase 1 model fixes
| Add ExitInterview model + ExitRequest + ClearanceTask | Delivers: REQ-EXIT-01, REQ-EXIT-02, REQ-EXIT-03, REQ-EXIT-04, REQ-EXIT-05 | 3-4 days | Phase 1 model fixes
| Add SystemConfig model + cost-per-hire / utilization thresholds | Delivers: SA-4 | 1-2 days | None
| Add recruitmentBudget + hiringFrozen to Company/CompanyGroup | Delivers: TA-2 | 1 day | None
| Add isCritical flag to Separation + Tenant Admin oversight widget | Delivers: TA-4 | 1 day | None
| Add Vercel Cron + /api/cron routes (nudges, retention, triggers) | Delivers: REQ-PER-02, REQ-SEC-10 (purge), REQ-EXIT-02 (automation) | 2-3 days | Phase 2 model fixes
Phase 3 — AI | Replace mock parse_resume + score_candidates with real ZAI calls | Delivers: REQ-REC-04, REQ-REC-05 | 3-4 days | Candidate model
| Add /api/capacity-ai route for burnout/under-allocation analysis | Delivers: REQ-PM-05 | 2-3 days | Utilization model
| Add sentiment analysis to /api/exit-interview POST | Delivers: REQ-EXIT-06 | 1-2 days | ExitInterview model
| Add /api/tenant-admin/ai-insights for deadline-miss predictions | Delivers: TA-5 | 2-3 days | Utilization + Invoice models
| Add ZAI auto-translation for job postings + client feedback | Delivers: REQ-REC-06, REQ-PER-03 | 2-3 days | next-intl
Phase 4 — UX | Build /dashboard/gantt with frappe-gantt | Delivers: REQ-PM-04 | 3-4 days | None
| Build Tenant Admin cross-company allocation UI with @dnd-kit | Delivers: TA-1, REQ-PM-03 | 3-4 days | None
| Build Super Admin Project Profitability dashboard | Delivers: SA-2 | 2-3 days | Invoice + convertCurrency
| Build Super Admin impersonation (context swap) UI with audit drill-down | Delivers: SA-3 (full) | 2-3 days | None
| Build PDF generation for Offer Letters + Service/Relieving Letters | Delivers: REQ-ONB-01, REQ-EXIT-08 | 3-4 days | Compliance rules engine
| Add admin_desk category to OnboardingTask + wire to AssetAssignment | Delivers: REQ-ONB-02 (full) | 1-2 days | None
| Fork /api/ai-chat into /api/onboarding-buddy with persona + KB | Delivers: REQ-ONB-03 (full) | 2 days | next-intl
| Add Client dropdown to Project create/edit form | Delivers: REQ-PM-01 (full) | 0.5 days | None
| Add ClientFeedback model + multi-lingual portal | Delivers: REQ-PER-03 | 2-3 days | next-intl
| Add severance + pro-rated bonus + auto-calc from LeaveBalance to FNFCalculation | Delivers: REQ-EXIT-07 (full) | 2 days | None
Phase Summary:
Phase 1 — Stabilize | 6 tasks
Phase 2 — Foundations | 9 tasks
Phase 3 — AI | 5 tasks
Phase 4 — UX | 10 tasks